## Strategy Map
2026 Vehicle Development Division — KPI Cascade Strategy
Category | Area | Weight | Key Description | Icon | # Team KPIs
Business (80%) | Local Spec Competitiveness | 25% | List local specs for 26-27 MY vehicles, mid/long-term roadmap, prioritize with regional teams | 🎯 | 3
| Economic New Tech Development | 20% | Locally-led new tech, Namyang collab items, motor localization & parts localization | 🔬 | 3
| Development Robustness | 20% | Crash review, DPA checklist, EO-based preventive design, ESIR schedule, drawing completeness | 🛡️ | 5
| Parts Commonization & Pre SR Process | 20% | L1 master list → purchase price → new vs C/O comparison → design counter-proposal process for all models | 🔄 | 4
| CCW Activities (Cost Reduction) | 15% | Continuous cost reduction activities for production vehicles | 💰 | 2
People (20%) | Talent Development | 100% | SW talent, PCL, E2E, manuals, culture survey, IIT seminar, tech show, training, commercial center support | 🎓 | 10

## Action Plans
2026 Vehicle Dev. — Team Action Plans
Team: Author: Date:
Parent KPI (Area) | Action Title | Icon | Description / Output | Owner | Target | Unit | Priority | Start Date | Due Date | Weight (0~1) | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5
Local Spec Competitiveness | List local specs for 26-27MY vehicles | 📋 | [Output: Spec List Excel] Compile local spec status per vehicle model & gap analysis |  | 1 | report | high | 2026-01-06 | 2026-03-31 | 0.35 | Collect current specs by model | Gap analysis vs competitors | Prioritize with regional VoC | Finalize & distribute list
Local Spec Competitiveness | Mid/long-term spec application roadmap | 🗺️ | [Output: Roadmap PPT] Master plan for local spec application across 28-30MY models |  | 1 | report | high | 2026-02-01 | 2026-05-31 | 0.35 | Collect benchmarking data (India/SEA) | Cost-benefit analysis per spec | Build priority matrix by model | Draft roadmap & internal review | Finalize roadmap
Local Spec Competitiveness | Regional coordination & priority alignment | 🤝 | [Output: Agreed minutes] Coordinate with regional teams to align spec priorities |  | 4 | sessions | medium | 2026-01-15 | 2026-06-30 | 0.3 | Finalize regional contact list | 1st meeting (status sharing) | 2nd meeting (priority discussion) | Final agreement & distribute minutes
Economic New Tech Development | Locally-led new technology items | 🔬 | [Output: Tech validation report] Discover & PoC locally-led new tech items |  | 3 | items | high | 2026-01-06 | 2026-06-30 | 0.4 | List new tech candidates | Feasibility analysis & prioritization | PoC plan & execution | PoC result report | Mass production applicability assessment
Economic New Tech Development | Namyang collaboration tech items | 🔗 | [Output: Joint dev report] Progress on joint tech development with Namyang R&D |  | 2 | items | high | 2026-02-01 | 2026-06-30 | 0.35 | Confirm collab items & define R&R | 1st interim review (tech review) | Prototype/simulation validation | Final report & mass production transfer decision
Economic New Tech Development | Motor & parts localization | 🏭 | [Output: Localization status table] Motor localization & key parts local sourcing |  | 2 | items | medium | 2026-03-01 | 2026-06-30 | 0.25 | Select parts for localization | Local supplier sourcing & tech evaluation | Prototype manufacturing & QC | Cost comparison analysis report
Development Robustness | Crash technology exchange meetings | 💥 | [Output: Meeting report] Regular crash tech exchange sessions & know-how sharing |  | 4 | sessions | high | 2026-01-15 | 2026-06-30 | 0.2 | Establish annual schedule | 1st exchange meeting & summary | Derive improvements & action plan | 2nd exchange meeting | Annual performance summary
Development Robustness | Strengthen DPA checklist | ✅ | [Output: Enhanced DPA checklist] Improve existing DPA checklist & apply to models |  | 1 | report | high | 2026-02-01 | 2026-04-30 | 0.2 | Analyze current DPA issues | Benchmark best practices | Derive improvements & revise checklist | Pilot model application & validation | Full model rollout
Development Robustness | EO-based preventive design before drawing release | 🔍 | [Output: Preventive design guide] Build EO case DB & pre-release prevention process |  | 1 | report | high | 2026-01-15 | 2026-05-31 | 0.2 | Collect & classify EO cases (2 years) | Draft prevention design guide | Cross-team review & feedback | Finalize pre-release check process | Distribute guide & training
Development Robustness | Strengthen ESIR schedule management | 📅 | [Output: Process improvement plan] Improve ESIR schedule compliance rate |  | 95 | % | medium | 2026-02-01 | 2026-06-30 | 0.2 | Analyze current ESIR compliance rate | Identify delay causes & improvement plan | Build management dashboard | Monthly monitoring operation
Development Robustness | Improve drawing completeness | 📐 | [Output: Drawing quality report] Improve drawing completeness metrics |  | 90 | % | high | 2026-01-06 | 2026-06-30 | 0.2 | Define completeness KPI metrics | Measure current level & gap analysis | Drive team-level improvements | Monthly completeness monitoring | Verify target achievement & report
Parts Commonization & Pre SR Process | Create Level-1 master parts list | 📊 | [Output: Master list Excel] Level-1 parts master list based on base vehicle |  | 1 | report | critical | 2026-01-15 | 2026-03-31 | 0.3 | Select base vehicle & obtain BOM | Organize L1 parts list | Map specs/drawing numbers per part | Internal validation & finalization
Parts Commonization & Pre SR Process | Purchase price & new vs C/O comparison | 💹 | [Output: Comparison table] Compare new development cost vs C/O cost & calculate savings |  | 1 | report | high | 2026-03-01 | 2026-05-15 | 0.3 | Collect purchase prices from master list | Estimate new development cost | Calculate C/O application cost | Create savings comparison table | Executive report
Parts Commonization & Pre SR Process | Build design counter-proposal process | 🔄 | [Output: Process guide] Establish pre-design-selection counter-proposal process for all models |  | 1 | report | high | 2026-02-01 | 2026-05-31 | 0.25 | Analyze KS2 counter-proposal cases | Draft standard process | Pilot model application & feedback | Finalize process & distribute guide | All-model kickoff
Parts Commonization & Pre SR Process | Commonization performance monitoring | 📈 | [Output: Monthly dashboard] Track commonization progress & savings monthly |  | 6 | reports | medium | 2026-03-01 | 2026-06-30 | 0.15 | Design monitoring KPIs & dashboard | Build monthly data collection system | Publish 1st report | 3-month cumulative performance analysis
CCW Activities (Cost Reduction) | Achieve production vehicle CCW targets | 💰 | [Output: CCW performance report] Drive cost reduction activities & track performance |  | 100 | % | high | 2026-01-06 | 2026-06-30 | 0.6 | Confirm CCW targets per model | Q1 cost reduction activities & tally | Midpoint review & supplemental plan | Q2 cost reduction activities | H1 comprehensive performance report
CCW Activities (Cost Reduction) | Cost reduction idea generation & sharing | 💡 | [Output: Idea DB] Collect cost reduction ideas & share best practices |  | 20 | ideas | medium | 2026-02-01 | 2026-06-30 | 0.4 | Monthly idea collection by team | Build idea database | Select & share best practices | Create execution plan for applicable items
Talent Development | SW talent development program | 💻 | [Output: Training status table] Operate SW competency training & manage completion rate |  | 90 | % | high | 2026-01-15 | 2026-06-30 | 0.12 | Confirm trainees & courses | Establish training schedule | Conduct training (quarterly) | Monitor completion rate
Talent Development | PCL system operation | 🔧 | [Output: PCL operation report] Stable PCL system operation & usage improvement |  | 1 | report | medium | 2026-01-06 | 2026-06-30 | 0.1 | Review current PCL status | Identify improvements needed | System update & training | Usage monitoring
Talent Development | E2E (Error to Excellence) activities | 🎯 | [Output: E2E case book] Convert error cases to excellence cases & share |  | 10 | cases | medium | 2026-02-01 | 2026-06-30 | 0.1 | Collect error cases by team | Root cause analysis & improvement plan | Apply improvements & verify | Compile excellence case book
Talent Development | Work manual creation | 📖 | [Output: Work manuals] Create standard process manuals for key tasks |  | 5 | manuals | medium | 2026-02-01 | 2026-06-30 | 0.08 | Select target processes | Assign owners & draft creation | Internal review & revision | Publish & distribute final manuals
Talent Development | Culture survey & improvement | 🏢 | [Output: Survey results & action plan] Conduct culture survey & drive improvements |  | 1 | report | medium | 2026-03-01 | 2026-06-30 | 0.1 | Design survey questions | Conduct survey & collect data | Analyze results & identify improvements | Execute improvement activities | Plan follow-up survey
Talent Development | IIT professor invited seminar | 🎓 | [Output: Seminar report] Host technology seminars with IIT professors |  | 2 | sessions | medium | 2026-02-15 | 2026-06-30 | 0.1 | Select topics & invite professors | Confirm schedule & recruit participants | Host seminar | Summarize results & discuss collaboration
Talent Development | Supplier & system tech shows | 🏗️ | [Output: Tech show report] Host supplier/system-level tech exhibitions |  | 2 | events | medium | 2026-03-01 | 2026-06-30 | 0.1 | Select topics & participating suppliers | Confirm schedule & booth setup | Host tech show | Select outstanding tech & review application
Talent Development | General & specialized training | 📚 | [Output: Training record] Operate general competency + team-specific training |  | 10 | sessions | medium | 2026-01-15 | 2026-06-30 | 0.1 | Establish training courses & schedule | Q1 training delivery | Midpoint completion check | Q2 training delivery | H1 training performance report
Talent Development | Design robustness training | 🛡️ | [Output: Training completion status] Operate design quality robustness training |  | 4 | sessions | high | 2026-02-01 | 2026-06-30 | 0.1 | Design training curriculum | Arrange instructors & confirm schedule | Deliver training (quarterly) | Evaluate training effectiveness
Talent Development | Commercial center (B04) support | 🚛 | [Output: Support performance report] Technical support for B04 vehicle development |  | 1 | report | medium | 2026-01-06 | 2026-06-30 | 0.1 | Define support scope & R&R | Execute technical support activities | Midpoint review & issue sharing | Complete support & summarize results

## Guide
Writing Guide
1. This template comes pre-filled with reference examples (gray italic).
Modify, delete, or add actions to fit your team's situation.
2. Required Elements (every action must include)
a) Owner — One responsible person
b) Due Date — YYYY-MM-DD format
c) Description/Output — Write as [Output: type] description
d) 3-5 Milestones — Verifiable interim checkpoints
3. Weight Rules
Weights of actions under the same parent KPI must sum to 1.0
4. Core Philosophy
"Break every task into achievable milestones."
Ensure every team member experiences achieving their own goals.
That is the power of organizational culture.
5. Submission: Fill in and reply with this file